## Feuil1
Infos dossiers |  |  |  |  | Facturation |  |  |  | Flux cash |  | Reconnaissance CAHT | [7 empty] | Jalon partie prestation | [8 empty] | Jalon Matériel | Jalon pose | Flux PCA/Compta
Code du dossier | Nom dans la compta | CA HT | CA TTC | Taux de TVA | Montants facturés HT | Montants facturés TTC | Reste à facturer | Contrôle logique | Montant encaissé | % d'encaissement sur le dossier | Part matériel estimée | Part pose estimée | Part prestations estimée | Marge théorique | Part CA total / matériel | Part CA total / pose | Part CA total / prestations | Verif CAHT | Visite technique validée | Demande d'urbanisme déposée | Demande de raccord. effectuée | Pose planifiée | Matériel commandé | Matériel posé | Chantier réceptionné | Mise en service réalisée | % de CAHT à reconnaitre en fonction du jalon pour la partie prestation | Avancement CA matériel | Avancement CA pose | CAHT à reconnaitre partie prestation | CAHT à reconnaitre partie matériel | CAHT à reconnaitre partie poste | PCA enregistré
03-EBREUIL-MON BRICO EBREUIL -354,220KWC | GATARD IMMOBILIER | 265665 | 318798 | 0,2 | 223158,59999999998 | 267790.32 | 51007.68 | OK | 223158,59999999998 | 0.7 |  |  |  |  | 0 | 0 | 0 | -265665 | OK | OK | ok | ok |  |  |  |  | 0 |  |  | 0 | 0 | 0
04-CASTELLANE-AUCHAN CASTELLANE 151,3KWC | - | 95319 | 114382.8 | 0,2 | 0 | 0 | 114382.8 | OK | 0 | 0 |  |  |  |  | 0 | 0 | 0 | -95319 | ok | [7 empty] | 0 |  |  | 0 | 0 | 0
10-PONT SAINTE MARIE-161,98KWC | - | 102047,4 | 122456.88 | 0,2 | 0 | 0 | 122456.88 | OK | 0 | 0 |  |  |  |  | 0 | 0 | 0 | -102047.4 | ok | [10 empty] | 0 | 0 | 0
13-MARSEILLE-SCI LOUISAVRAHAM 392,435KWC | - | 569030,8 | 682836.96 | 0,2 | 0 | 0 | 682836.96 | OK | 0 | 0 |  |  |  |  | 0 | 0 | 0 | -569030.8 | ok | [7 empty] | 0 |  |  | 0 | 0 | 0
14-AUDRIEU-SCEA DES CHAUDIERES 35,6KWC | - | 38870 | 46644 | 0,2 | 0 | 0 | 46644 | OK | 0 | 0 |  |  |  |  | 0 | 0 | 0 | -38870 | [8 empty] | 0 |  |  | 0 | 0 | 0
14-BRETTEVILLE SUR VAILLE-GOSSELIN OLIVIER 3KWC | - | 5445,5 | 5990.05 | 0,1 | 0 | 0 | 5990.05 | OK | 0 | 0 |  |  |  |  | 0 | 0 | 0 | -5445.5 | [8 empty] | 0 |  |  | 0 | 0 | 0
14-CROUAY-EARL LE CREULLET-34KWC | EARL LE CREULLET | 44321,3 | 53185.56 | 0,2 | 42547,78 | 51057.336 | 2128.224 | OK | 42547,78 | 0.79999 |  |  |  |  | 0 | 0 | 0 | -44321.3 | ok | ok | ok | ok | ok | ok |  |  | 0 |  |  | 0 | 0 | 0
14-DEMOUVILLE-SCI DU LAIZON-36KWC BAT 1 | SCI DU LAIZON | 37900 | 45480 | 0,2 | 36384 | 43660.8 | 1819.2 | OK | 0 | 0 |  |  |  |  | 0 | 0 | 0 | -37900 | ok | ok | ok | ok |  |  |  |  | 0 |  |  | 0 | 0 | 0
14-DEMOUVILLE-SCI DU LAIZON-36KWC BAT 2 | SCI DU LAIZON | 37900 | 45480 | 0,2 | 13644 | 16372.8 | 29107.2 | OK | 0 | 0 |  |  |  |  | 0 | 0 | 0 | -37900 | ok | ok | ok | ok |  |  |  |  | 0 |  |  | 0 | 0 | 0
14-DOUVRES LA DELIVNARDES-CASSIGNEUL LUDOVIC 99,68KWC | - | 78480 | 94176 | 0,2 | 9417,6 | 11301.12 | 82874.88 | OK | 0 | 0 |  |  |  |  | 0 | 0 | 0 | -78480 | OK | OK | OK | [5 empty] | 0 |  |  | 0 | 0 | 0
14-GRANDCAMP MAISY-GAEC DES ROUGES TERRES-237,185KWC | GAEC DES ROUGES TERRES | 194296,2 | 233155.44 | 0,2 | 186524,35 | 223829.22 | 9326.22 | OK | 186524,35 | 0.8 |  |  |  |  | 0 | 0 | 0 | -194296.2 | OK | OK | OK | OK |  |  |  |  | 0 |  |  | 0 | 0 | 0
14-GUERON-SCEA DE LA BOUFFARDIERE 17,8KWC | SCEA DE LA BOUFFARDIERE | 27122 | 32546.4 | 0,2 | 3254,64 | 3905.568 | 28640.832 | OK | 0 | 0 |  |  |  |  | 0 | 0 | 0 | -27122 | OK | [7 empty] | 0 |  |  | 0 | 0 | 0
14-LE PRE D AUGE-ANDRE JEAN CHARLES-24,92KWC | JEAN ANDRE | 33500 | 40200 | 0,2 | 12060 | 14472 | 25728 | OK | 5000 | 0.12438 |  |  |  |  | 0 | 0 | 0 | -33500 | OK | OK | OK | [5 empty] | 0 |  |  | 0 | 0 | 0
14-LE PRE D AUGE-ANDRE JEAN CHARLES-156,64KWC | JEAN ANDRE | 77812,5 | 93375 | 0,2 | 9337,5 | 11205 | 82170 | OK | 0 | 0 |  |  |  |  | 0 | 0 | 0 | -77812.5 | OK | OK | OK | [5 empty] | 0 |  |  | 0 | 0 | 0
14-MEZIDON VALLEE D AUGE-MOINS-190,015KWC | PIERRICK MOINS | 161732,3 | 194078.76 | 0,2 | 58223,59 | 69868.308 | 124210.452 | OK | 0 | 0 |  |  |  |  | 0 | 0 | 0 | -161732.3 | OK | OK | OK | [5 empty] | 0 |  |  | 0 | 0 | 0
14-MONTIGNY-EMILIE MASSU 99KWC | EMILIE MASSU | 85000 | 102000 | 0,2 | 30600 | 36720 | 65280 | OK | 30600 | 0.3 |  |  |  |  | 0 | 0 | 0 | -85000 | OK | OK | OK | OK |  |  |  |  | 0 |  |  | 0 | 0 | 0
14-MONTIGNY-EMILIE MASSU 99KWC 2 | EMILIE MASSU | 77970 | 93564 | 0,2 | 9356,4 | 11227.68 | 82336.32 | OK | 9356,4 | 0.1 |  |  |  |  | 0 | 0 | 0 | -77970 | OK | OK | OK | [5 empty] | 0 |  |  | 0 | 0 | 0
14-NOTRE DAME D'ESTREES-GAEC DE LA VALLEE 99,68KWC | GAEC DE LA VALLEE | 94438 | 113325.6 | 0,2 | 33997,68 | 40797.216 | 72528.384 | OK | 11300 | 0.099713 |  |  |  |  | 0 | 0 | 0 | -94438 | OK | OK | OK | [5 empty] | 0 |  |  | 0 | 0 | 0
14-PLUMETOT-EARL DES PERELLES-249,48KWC | EARL LES PERRELLES | 180000 | 216000 | 0,2 | 216000 | 259200 | -43200 | OK | 205200 | 0.95 |  |  |  |  | 0 | 0 | 0 | -180000 | OK | OK | OK | OK | OK | OK | OK | OK | 0 |  |  | 0 | 0 | 0
14-ST AUBIN SUR MER-PADET JEROME 3KWC | Jerome PADET | 5445,5 | 5990.05 | 0,1 | 1800 | 1980 | 4010.05 | OK | 1800 | 0.3005 |  |  |  |  | 0 | 0 | 0 | -5445.5 | OK | OK | OK | OK |  |  |  |  | 0 |  |  | 0 | 0 | 0
16-CHATEAUBERNARD-SCI TOUT BLANC-287,47KWC | SCI TOUT BLANC | 197774,3 | 237329.16 | 0,2 | 71198,75 | 85438.5 | 151890.66 | OK | 0 | 0 |  |  |  |  | 0 | 0 | 0 | -197774.3 | OK | OK | OK | [5 empty] | 0 |  |  | 0 | 0 | 0
16-CHATEAUBERNARD-SCI TOUT BLANC-36 KWC | SCI TOUT BLANC | 38870 | 46644 | 0,2 | 13993,2 | 16791.84 | 29852.16 | OK | 0 | 0 |  |  |  |  | 0 | 0 | 0 | -38870 | OK | OK | OK | [5 empty] | 0 |  |  | 0 | 0 | 0
16-COGNAC-SARL QUAD BIKE 41KWC | SARL QUAD BIKE EVASION | 51824,5 | 62189.4 | 0,2 | 18656,82 | 22388.184 | 39801.216 | OK | 0 | 0 |  |  |  |  | 0 | 0 | 0 | -51824.5 | OK | OK | OK | [5 empty] | 0 |  |  | 0 | 0 | 0
16-COGNAC-SCI LA ROMAINE 234KWC | SCI LA ROMAINE | 168428,3 | 202113.96 | 0,2 | 60634,19 | 72761.028 | 129352.932 | OK | 0 | 0 |  |  |  |  | 0 | 0 | 0 | -168428.3 | OK | OK | OK | [5 empty] | 0 |  |  | 0 | 0 | 0
16-GENSAC LA PALLUE-SCI LA PETITE CHAMPAGNE 99,68KWC | SCI DE LA PETITE CHAMPAGNE | 100520 | 120624 | 0,2 | 36187,2 | 43424.64 | 77199.36 | OK | 12062,4 | 0.1 |  |  |  |  | 0 | 0 | 0 | -100520 | OK | OK | OK | [5 empty] | 0 |  |  | 0 | 0 | 0
17-BERNEUIL-EARL MITTARD SEBASTIEN-494,5KWC | DE LA SEUGNE | 443895 | 532674 | 0,2 | 426139,2 | 511367.04 | 21306.96 | OK | 426139,2 | [5 empty] | 0 | 0 | 0 | -443895 | OK | OK | OK | OK | [7 empty] | 0 | 0 | 0
17-PERIGNY-SOFINOX-86 KWC | SOFINOX PROD | 68467,5 | 82161 | 0,2 | 24648,300000000003 | 29577.96 | 52583.04 | OK | 24648,300000000003 | [5 empty] | 0 | 0 | 0 | -68467.5 | OK | OK | OK | OK | [7 empty] | 0 | 0 | 0
27-BREUX SUR AVRE-DOMAINE DE L'AVRE-9KWC | LE DOMAINE DE L'AVRE | 12491,7 | 14990.04 | 0,2 | 4497 | 5396.4 | 9593.64 | OK | 4497 | [5 empty] | 0 | 0 | 0 | -12491.7 | OK | OK | OK | [8 empty] | 0 | 0 | 0
27-LA HAYE DE CALLEVILLE-GAEC DE LA BOURDERIE-9KWC | GAEC DE LA BOURDERIE | 12491,7 | 14990.04 | 0,2 | 4497 | 5396.4 | 9593.64 | OK | 0 | [5 empty] | 0 | 0 | 0 | -12491.7 | OK | OK | [9 empty] | 0 | 0 | 0
27-LE THUIT DE L'OISON-ETRIER DU ROUMOIS 3KWC | - | 5445,5 | 5990.05 | 0,1 | 0 | 0 | 5990.05 | OK | 0 | [5 empty] | 0 | 0 | 0 | -5445.5 | OK | [10 empty] | 0 | 0 | 0
29-PLONEOUR LANVERN-SCI NJT 99,68KWC | - | 78480 | 94176 | 0,2 | 0 | 0 | 94176 | OK | 0 | [5 empty] | 0 | 0 | 0 | -78480 | OK | [10 empty] | 0 | 0 | 0
29-PLOUDALMEZEAU-GAEC DE KERSIMON 87KWC | GAEC DE KERSIMON | 90050 | 108060 | 0,2 | 86448 | 103737.6 | 4322.4 | OK | 86448 | [5 empty] | 0 | 0 | 0 | -90050 | OK | OK | OK | OK | [7 empty] | 0 | 0 | 0
29-PLOUDALMEZEAU-GAEC DE KERSIMON 90KWC | GAEC DE KERSIMON | 100109 | 120130.8 | 0,2 | 96104,64 | 115325.568 | 4805.232 | OK | 12013,08 | [5 empty] | 0 | 0 | 0 | -100109 | OK | OK | OK | OK | [7 empty] | 0 | 0 | 0
35-ARGENTRES DU PLESSIS-BIGNON 6KWC | BRUNO BIGNON | 8741,7 | 10490.04 | 0,2 | 3147,01 | 3776.412 | 6713.628 | OK | 0 | [5 empty] | 0 | 0 | 0 | -8741.7 | OK | OK | OK | [8 empty] | 0 | 0 | 0
35-BRUZ-EVAIN JOUBERT-8,9kWc | EVAIN JOUBERT | 12491,7 | 14990.04 | 0,2 | 4497 | 5396.4 | 9593.64 | OK | 4497 | [5 empty] | 0 | 0 | 0 | -12491.7 | OK | OK | OK | OK | [7 empty] | 0 | 0 | 0
37-COURCOUE-BLANC OLIVIER 9KWC | LE PUITS DORE | 10875 | 13050 | 0,2 | 3915 | 4698 | 8352 | OK | 3915 | [5 empty] | 0 | 0 | 0 | -10875 | OK | OK | OK | OK | [7 empty] | 0 | 0 | 0
37-MONTLOUIS SUR LOIRE-CHRISTOPHE BERTHIER 499,735KWC | - | 373832,2 | 448598.64 | 0,2 | 0 | 0 | 448598.64 | OK | 0 | [5 empty] | 0 | 0 | 0 | -373832.2 | [11 empty] | 0 | 0 | 0
37-ST QUENTIN SUR INDROIS-VRIGNAUD 232KWC | - | 160562,8 | 192675.36 | 0,2 | 0 | 0 | 192675.36 | OK | 0 | [5 empty] | 0 | 0 | 0 | -160562.8 | OK | OK | [9 empty] | 0 | 0 | 0
37-YZEURES SUR CREUSE-RAVINET -11,57KWC | Philippe RAVINET | 25184 | 30220.8 | 0,2 | 24176,64 | 29011.968 | 1208.832 | OK | 9066,24 | [5 empty] | 0 | 0 | 0 | -25184 | OK | OK | OK | OK | [7 empty] | 0 | 0 | 0
37-YZEURES SUR CREUSE-SAS COPAHO-11,57KWC | COMPAGNIE PARISIENNE D'HOTELLERIE | 25184 | 30220.8 | 0,2 | 24176,64 | 29011.968 | 1208.832 | OK | 9066,24 | [5 empty] | 0 | 0 | 0 | -25184 | OK | OK | OK | OK | [7 empty] | 0 | 0 | 0
37-YZEURES SUR CREUSE-SNC RELAIS DE LA MOTTE 26,255KWC | SNC LE RELAIS DE LA MOTHE | 38496,2 | 46195.44 | 0,2 | 13858,63 | 16630.356 | 29565.084 | OK | 0 | [5 empty] | 0 | 0 | 0 | -38496.2 | OK | OK | OK | [8 empty] | 0 | 0 | 0
38-ST BARTHELEMY-INTERMARCHE 289,695KWC | - | 182508 | 219009.6 | 0,2 | 0 | 0 | 219009.6 | OK | 0 | [5 empty] | 0 | 0 | 0 | -182508 | [11 empty] | 0 | 0 | 0
41-LA FERTE BEAUHARNAIS-GUEMON -6KWC | JEAN-PIERRE GUEMON | 9575 | 11490 | 0,2 | 3447 | 4136.4 | 7353.6 | OK | 0 | [5 empty] | 0 | 0 | 0 | -9575 | OK | OK | [9 empty] | 0 | 0 | 0
43-CRAPONNE SUR ARZON-CARROSSERIE DE L'ARZON-34KWC | CARROSSERIE DE L'ARZON | 43442,67 | 52131.204 | 0,2 | 52131,200000000004 | 62557.44 | -10426.236 | OK | 50131,200000000004 | [5 empty] | 0 | 0 | 0 | -43442.67 | OK | OK | OK | OK | OK | OK | OK | OK |  |  |  | 0 | 0 | 0
44-ISSE-SCEA GAUTREAU POIRIER-6,23KWC | SCEA GAUTREAU POIRIER | 7916,67 | 9500.004 | 0,2 | 9500,07 | 11400.084 | -1900.08 | OK | 7850 | [5 empty] | 0 | 0 | 0 | -7916.67 | OK | OK | OK | OK | OK | OK | OK | OK |  |  |  | 0 | 0 | 0
44-NANTES-GEORGES AERTES 6KWC | GEORGES AERTS | 8741,7 | 10490.04 | 0,2 | 3147,01 | 3776.412 | 6713.628 | OK | 3147,01 | [5 empty] | 0 | 0 | 0 | -8741.7 | OK | OK | OK | OK | moitié | [6 empty] | 0 | 0 | 0
44-ST MICHEL CHEF CHEF-HUCHET-6KWC | GAETAN HUCHET | 8741,7 | 10490.04 | 0,2 | 3147 | 3776.4 | 6713.64 | OK | 3147 | [5 empty] | 0 | 0 | 0 | -8741.7 | OK | OK | OK | OK | 0,8 | [6 empty] | 0 | 0 | 0
44-ST VIAUD-BOISSERPE 3KWC | Gildas BOISSERPE | 5445,45 | 5989.995 | 0,1 | 5990,05 | 6589.055 | -599.06 | OK | 5747,0185 | [5 empty] | 0 | 0 | 0 | -5445.45 | OK | OK | OK | OK | OK | OK | OK | OK |  |  |  | 0 | 0 | 0
49-CORZE-STPA 240,3KWC | - | 172727 | 207272.4 | 0,2 | 0 | 0 | 207272.4 | OK | 0 | [5 empty] | 0 | 0 | 0 | -172727 | [11 empty] | 0 | 0 | 0
49-CORZE-STPA 365,79KWC | - | 250578,5 | 300694.2 | 0,2 | 0 | 0 | 300694.2 | OK | 0 | [5 empty] | 0 | 0 | 0 | -250578.5 | [11 empty] | 0 | 0 | 0
49-DOUE EN ANJOU-QUINCAILLERIE DOUESSINE-181,560KWC | GATARD IMMOBILIER | 258508,8 | 310210.56 | 0,2 | 217147,4 | 260576.88 | 49633.68 | OK | 217147,396 | [5 empty] | 0 | 0 | 0 | -258508.8 | OK | OK | OK | OK | [7 empty] | 0 | 0 | 0
49-DOUE EN ANJOU-QUINCAILLERIE DOUESSINE-499,735KWC | GATARD IMMOBILIER | 374801,3 | 449761.56 | 0,2 | 314833,05000000005 | 377799.66 | 71961.9 | OK | 314833,04600000003 | [5 empty] | 0 | 0 | 0 | -374801.3 | OK | OK | OK | OK | [7 empty] | 0 | 0 | 0
49-MORANNES SUR SARTHE DAUMERAY-SCI DE LA FONTAINE DE SUIE-9KWC | SCI LA FONTAINE DE SUIE | 12075 | 14490 | 0,2 | 4347 | 5216.4 | 9273.6 | OK | 4347 | [5 empty] | 0 | 0 | 0 | -12075 | OK | oK | OK | OK | [7 empty] | 0 | 0 | 0
49-RIVES DU LOIR EN ANJOU-ECURIE AMP-312,835KWC | ANNE MARIE POIRIER | 242546,3 | 291055.56 | 0,2 | 232844,15000000002 | 279412.98 | 11642.58 | OK | 0 | [5 empty] | 0 | 0 | 0 | -242546.3 | OK | OK | OK | OK | [7 empty] | 0 | 0 | 0
49-SAUMUR-DELKO SAUMUR 58,74KWC | - | 44055 | 52866 | 0,2 | 0 | 0 | 52866 | OK | 0 | [5 empty] | 0 | 0 | 0 | -44055 | [11 empty] | 0 | 0 | 0
49-SEVREMOINE-AKH 159,31KWC | - | 167663,2 | 201195.84 | 0,2 | 0 | 0 | 201195.84 | OK | 0 | [5 empty] | 0 | 0 | 0 | -167663.2 | OK | [10 empty] | 0 | 0 | 0
49-ST CHRISTOPHE DU BOIS-GUITTON OLIVIER 9KWC | OLIVIER GUITTON | 12075 | 14490 | 0,2 | 4347 | 5216.4 | 9273.6 | OK | 4347 | [5 empty] | 0 | 0 | 0 | -12075 | OK | OK | OK | OK | [7 empty] | 0 | 0 | 0
50-AUVERS-GAEC DU MOULINET-99,680KW 1 | GAEC DU MOULINET | 72669,70000000001 | 87203.64 | 0,2 | 69762,9 | 83715.48 | 3488.16 | OK | 5304,17 | [5 empty] | 0 | 0 | 0 | -72669.7 | OK | OK | OK | OK | [7 empty] | 0 | 0 | 0
50-AUVERS-GAEC DU MOULINET-99,680KW 2 | GAEC DU MOULINET | 92488,7 | 110986.44 | 0,2 | 33295,94 | 39955.128 | 71031.312 | OK | 0 | [5 empty] | 0 | 0 | 0 | -92488.7 | OK | OK | OK | OK | [7 empty] | 0 | 0 | 0
50-GROSVILLE-GAUTIER THIERRY 5,785KWC | Thierry GAUTIER | 11328,4 | 13594.08 | 0,2 | 4078,22 | 4893.864 | 8700.216 | OK | 4078,22 | [5 empty] | 0 | 0 | 0 | -11328.4 | OK | OK | OK | OK | [7 empty] | 0 | 0 | 0
50-MARIGNY LE LOZON-ROGER BERNARD 3KWC | Roger BERNARD | 5718,2 | 6290.02 | 0,1 | 1887 | 2075.7 | 4214.32 | OK | 1887 | [5 empty] | 0 | 0 | 0 | -5718.2 | OK | OK | OK | OK | [7 empty] | 0 | 0 | 0
50-PERIERS-LEFORESTIER JEREMY-35,670KWC | Jérémy Leforestier | 46371 | 55645.2 | 0,2 | 33387,119999999995 | 40064.544 | 15580.656 | OK | 4680 | [5 empty] | 0 | 0 | 0 | -46371 | OK | OK | OK | [8 empty] | 0 | 0 | 0
50-ST AUBIN DE TERREGATTE-MOREL 4,45KWC | CHRISTIAN MOREL | 6483,21 | 7779.852 | 0,2 | 2333,95 | 2800.74 | 4979.112 | OK | 0 | [5 empty] | 0 | 0 | 0 | -6483.21 | OK | [10 empty] | 0 | 0 | 0
50-ST GEORGES DE LA RIVIERE-GAEC DES COTTES-486,385KWC | GAEC DES COTTES | 373708,8 | 448450.56 | 0,2 | 134535,16999999998 | 161442.204 | 287008.356 | OK | 0 | [5 empty] | 0 | 0 | 0 | -373708.8 | OK | OK | OK | [8 empty] | 0 | 0 | 0
50-ST PIERRE D'ARTHEGLISE-LERICHE BENJAMIN 17,8KWC | Benjamin LERICHE | 28000 | 33600 | 0,2 | 3360 | 4032 | 29568 | OK | 0 | [5 empty] | 0 | 0 | 0 | -28000 | OK | [10 empty] | 0 | 0 | 0
50-YVETOT BOCAGE-GAEC LA HAULLE DE LYS 17,8KWC | GAEC DE LA HAULLE DE LYS | 27000 | 32400 | 0,2 | 9720 | 11664 | 20736 | OK | 0 | [5 empty] | 0 | 0 | 0 | -27000 | OK | [10 empty] | 0 | 0 | 0
51-VRIGNY-SARL FONTBELLE-155,8KWC | FONTBELLE | 135673,92 | 162808.704 | 0,2 | 162807,53999999998 | 195369.048 | -32560.344 | OK | 154666,6124 | [5 empty] | 0 | 0 | 0 | -135673.92 | OK | OK | OK | OK | OK | OK | OK | OK |  |  |  | 0 | 0 | 0
53-LOUVERNE-PUBLIDECOR CAMELEON-76,54KWC | PUBLI DECOR | 110217,6 | 132261.12 | 0,2 | 39678,34 | 47614.008 | 84647.112 | OK | 39678,335999999996 | [5 empty] | 0 | 0 | 0 | -110217.6 | OK | OK | OK | OK | [7 empty] | 0 | 0 | 0
56-MALESTROIT-GROUPE YCS-211,375KWC | GROUPE YCS | 126825 | 152190 | 0,2 | 121752 | 146102.4 | 6087.6 | OK | 0 | [5 empty] | 0 | 0 | 0 | -126825 | OK | OK | OK | OK | [7 empty] | 0 | 0 | 0
61-FLERS-SARL PAINT-231,4KWC | SARL PAINT | 189726 | 227671.2 | 0,2 | 68301,36 | 81961.632 | 145709.568 | OK | 0 | [5 empty] | 0 | 0 | 0 | -189726 | OK | OK | OK | [8 empty] | 0 | 0 | 0
61-L'ORLAY L'ABBAYE-SCEA DU PERIER 35,6KWC | - | 38870 | 46644 | 0,2 | 0 | 0 | 46644 | OK | 0 | [5 empty] | 0 | 0 | 0 | -38870 | [11 empty] | 0 | 0 | 0
61-LIUGE SUR MAIRE-EARL DES PETITES ROSES 499,735KWC | EARL DES PETITES ROSES | 368884,3 | 442661.16 | 0,2 | 132798,35 | 159358.02 | 283303.14 | OK | 44266,12 | [5 empty] | 0 | 0 | 0 | -368884.3 | OK | OK | OK | [8 empty] | 0 | 0 | 0
61-STE GAUBURGE STE COLOMBE-UNE FILANTE 99,68KWC | UNE FILANTE | 90448 | 108537.6 | 0,2 | 10853,76 | 13024.512 | 95513.088 | OK | 0 | [5 empty] | 0 | 0 | 0 | -90448 | [11 empty] | 0 | 0 | 0
61-ST AUBIN DE BONNEVAL-GAEC LA RENARDIERE 29,815KWC | GAEC DE LA RENARDIERE | 41741 | 50089.2 | 0,2 | 15026,76 | 18032.112 | 32057.088 | OK | 0 | [5 empty] | 0 | 0 | 0 | -41741 | OK | OK | OK | [8 empty] | 0 | 0 | 0
61-ST BOMER LES FORGES-SILANDRE BRANDON 96KWC | - | 75945 | 91134 | 0,2 | 0 | 0 | 91134 | OK | 0 | [5 empty] | 0 | 0 | 0 | -75945 | [11 empty] | 0 | 0 | 0
61-ST LEONARD DES PARCS-SCI LES ROUGES TERRES-414,295KWC | SOCIETE D'ENTRAINEMENT LOUIS BAUDRON | 319641,3 | 383569.56 | 0,2 | 115070,87 | 138085.044 | 245484.516 | OK | 0 | [5 empty] | 0 | 0 | 0 | -319641.3 | OK | OK | OK | [8 empty] | 0 | 0 | 0
61-TOUROUVRE AU PERCHE-CYRIL LE FLOC H 28,035KWC | CYRIL LE FLOC'H | 40739 | 48886.8 | 0,2 | 14666,04 | 17599.248 | 31287.552 | OK | 0 | [5 empty] | 0 | 0 | 0 | -40739 | OK | [10 empty] | 0 | 0 | 0
63-MURAT LE QUAIRE-DE FALVARD-100KWC | Stéphane DE FALVARD | 88182,4 | 105818.88 | 0,2 | 84655,09 | 101586.108 | 4232.772 | OK | 84655,094 | [5 empty] | 0 | 0 | 0 | -88182.4 | OK | OK | OK | OK | [7 empty] | 0 | 0 | 0
63-PONTAUMUR-MON BRICO PONTAUMUR-121,040KWC | GATARD IMMOBILIER | 90780 | 108936 | 0,2 | 76255,2 | 91506.24 | 17429.76 | OK | 76255,2 | [5 empty] | 0 | 0 | 0 | -90780 | OK | OK | OK | OK | [7 empty] | 0 | 0 | 0
63-ST ELOY LES MINES-MON BRICO SAINT ELOY LES MINES-118,370KWC | GATARD IMMOBILIER | 88777,5 | 106533 | 0,2 | 101206,36 | 121447.632 | -14914.632 | OK | 101206,36 | [5 empty] | 0 | 0 | 0 | -88777.5 | OK | OK | OK | OK | OK | OK | [5 empty] | 0 | 0 | 0
66-AMELIE LES BAINS PALALDA-HOTEL LE CATALOGNE-41,800KWC | GATARD LOCATION | 31372,5 | 37647 | 0,2 | 37647 | 45176.4 | -7529.4 | OK | 35764,66 | [5 empty] | 0 | 0 | 0 | -31372.5 | OK | OK | OK | OK | OK | OK | OK |  |  |  |  | 0 | 0 | 0
69-TASSIN LA DEMI LUNE-SIOL 69-42,275KWC | SI DE L'OUEST LYONNAIS | 52336,3 | 62803.56 | 0,2 | 50242,85 | 60291.42 | 2512.14 | OK | 50242,85 | [5 empty] | 0 | 0 | 0 | -52336.3 | OK | OK | OK | OK | [7 empty] | 0 | 0 | 0
71-MONTCEAU LES MINES-CASINO 311,055KWC | - | 195965 | 235158 | 0,2 | 0 | 0 | 235158 | OK | 0 | [5 empty] | 0 | 0 | 0 | -195965 | [11 empty] | 0 | 0 | 0
72-DOUILLET-EARL LANGLAIS-6KWC | EARL LANGLAIS | 13061,25 | 15673.5 | 0,2 | 4702,0599999999995 | 5642.472 | 10031.028 | OK | 1000 | [5 empty] | 0 | 0 | 0 | -13061.25 | OK | OK | OK | OK | [7 empty] | 0 | 0 | 0
72-PRUILLE L EGUILLE-SARL PICHON FRERES 20,025KWC | PICHON FRERES | 28523,75 | 34228.5 | 0,2 | 24114,260000000002 | 28937.112 | 5291.388 | OK | 3500 | [5 empty] | 0 | 0 | 0 | -28523.75 | OK | OK | OK | OK | [7 empty] | 0 | 0 | 0
72-VILLAINE SOUS LUCE-BRIERE JEAN YVES 3KWC | - | 5445,45 | 5989.995 | 0,1 | 0 | 0 | 5989.995 | OK | 0 | [5 empty] | 0 | 0 | 0 | -5445.45 | [11 empty] | 0 | 0 | 0
74-DEMI QUARTIER-AUCHAN MEGEVE 269,67KWC | - | 169892 | 203870.4 | 0,2 | 0 | 0 | 203870.4 | OK | 0 | [5 empty] | 0 | 0 | 0 | -169892 | [11 empty] | 0 | 0 | 0
79-BRESSUIRE-MON BRICO BRESSUIRE-200,250KWC | GATARD IMMOBILIER | 150187,5 | 180225 | 0,2 | 171213,74 | 205456.488 | -25231.488 | OK | 126157,5 | [5 empty] | 0 | 0 | 0 | -150187.5 | OK | OK | OK | OK | OK | OK | [5 empty] | 0 | 0 | 0
79-CERIZAY-MON BRICO CERIZAY-170,88KWC | GATARD IMMOBILIER | 128160 | 153792 | 0,2 | 146102,4 | 175322.88 | -21530.88 | OK | 107654,4 | [5 empty] | 0 | 0 | 0 | -128160 | OK | OK | OK | OK | [7 empty] | 0 | 0 | 0
79-CHEF BOUTONNE-MON BRICO CHEF BOUTONNE-124,600KWC | GATARD IMMOBILIER | 93450 | 112140 | 0,2 | 78498 | 94197.6 | 17942.4 | OK | 44856 | [5 empty] | 0 | 0 | 0 | -93450 | OK | OK | OK | OK | [7 empty] | 0 | 0 | 0
79-COURLAY-LA COMBE MON BRICO-53,4KWC | SIMON GATARD | 40050 | 48060 | 0,2 | 19224 | 23068.8 | 24991.2 | OK | 0 | [5 empty] | 0 | 0 | 0 | -40050 | OK | OK | OK | [8 empty] | 0 | 0 | 0
79-MONCOUTANT SUR SEVRE-MON BRICO MONCOUTANT-45,84KWC | GATARD IMMOBILIER | 35518,25 | 42621.9 | 0,2 | 42621,899999999994 | 51146.28 | -8524.38 | OK | 34097,52 | [5 empty] | 0 | 0 | 0 | -35518.25 | OK | OK | OK | OK | OK | OK | OK |  |  |  |  | 0 | 0 | 0
79-MONCOUTANT SUR SEVRE-MON BRICO MONCOUTANT-72,980KWC | GATARD IMMOBILIER | 54735 | 65682 | 0,2 | 62178,96 | 74614.752 | -8932.752 | OK | 62178,96000000001 | [5 empty] | 0 | 0 | 0 | -54735 | OK | OK | OK | OK | OK | OK | [5 empty] | 0 | 0 | 0
79-NIORT-SARL BIARDEAU 9KWC | SOC BIARDEAU SA | 12641,130000000001 | 15169.356 | 0,2 | 4550,81 | 5460.972 | 9708.384 | OK | 4550,81 | [5 empty] | 0 | 0 | 0 | -12641.13 | OK | OK | OK | OK | 0,7 | [6 empty] | 0 | 0 | 0
79-SAUZE VAUSSAIS-MON BRICO SAUZE VAUSSAIS-499,84KWC | GATARD IMMOBILIER | 374801,3 | 449761.56 | 0,2 | 314835,26 | 377802.312 | 71959.248 | OK | 314835,256 | [5 empty] | 0 | 0 | 0 | -374801.3 | OK | OK | OK | OK | [7 empty] | 0 | 0 | 0
79-THOUARS-MON BRICO THOUARS-281,240KWC | GATARD IMMOBILIER | 210930 | 253116 | 0,2 | 177181,2 | 212617.44 | 40498.56 | OK | 177181,2 | [5 empty] | 0 | 0 | 0 | -210930 | OK | OK | OK | OK | [7 empty] | 0 | 0 | 0
81-LAVAUR-103,685KWC | - | 67395,3 | 80874.36 | 0,2 | 0 | 0 | 80874.36 | OK | 0 | [5 empty] | 0 | 0 | 0 | -67395.3 | [11 empty] | 0 | 0 | 0
85-BEAUVOIR SUR MER-UNISAP-409,64KWC S | UNISAP | 271356 | 325627.2 | 0,2 | 195375,59999999998 | 234450.72 | 91176.48 | OK | 195375,6 | [5 empty] | 0 | 0 | 0 | -271356 | OK | OK | OK | OK | [7 empty] | 0 | 0 | 0
85-BEAUVOIR SUR MER-UNISAP-409,64KWC O | UNISAP | 306525 | 367830 | 0,2 | 220698 | 264837.6 | 102992.4 | OK | 220698 | [5 empty] | 0 | 0 | 0 | -306525 | OK | OK | OK | OK | [7 empty] | 0 | 0 | 0
85-CHANTONNAY-MON BRICO CHANTONNAY-339,090KWC | GATARD IMMOBILIER | 254317,5 | 305181 | 0,2 | 213626,7 | 256352.04 | 48828.96 | OK | 213626,7 | [5 empty] | 0 | 0 | 0 | -254317.5 | OK | OK | OK | OK | [7 empty] | 0 | 0 | 0
85-FONTENAY LE COMTE-PRO BOIS-48KWC | PRO BOIS | 55833,33 | 66999.996 | 0,2 | 67000 | 80400 | -13400.004 | OK | 59200 | [5 empty] | 0 | 0 | 0 | -55833.33 | OK | OK | OK | OK | OK | OK | OK | OK |  |  |  | 0 | 0 | 0
85-LA CHATAIGNERAIE-MON BRICO LA CHATAIGNERAIE-239,410KWC | GATARD IMMOBILIER | 179557,5 | 215469 | 0,2 | 150828,3 | 180993.96 | 34475.04 | OK | 86187,6 | [5 empty] | 0 | 0 | 0 | -179557.5 | OK | OK | OK | Ok | [7 empty] | 0 | 0 | 0
85-LES SABLES D OLONNE-CHATODIS-434,28KWC | CHATODIS | 620000 | 744000 | 0,2 | 744000 | 892800 | -148800 | OK | 669600 | [5 empty] | 0 | 0 | 0 | -620000 | OK | OK | OK | OK | OK | OK | [5 empty] | 0 | 0 | 0
85-POUZAUGES-MON BRICO POUZAUGES-111,250KWC | GATARD IMMOBILIER | 83437,5 | 100125 | 0,2 | 70087,5 | 84105 | 16020 | OK | 70087,5 | [5 empty] | 0 | 0 | 0 | -83437.5 | OK | OK | OK | OK | [7 empty] | 0 | 0 | 0
85-ST FULGENT-MON BRICO SAINT FULGENT-206,035KWC | GATARD IMMOBILIER | 154526,3 | 185431.56 | 0,2 | 176159,96 | 211391.952 | -25960.392 | OK | 129802,08399999997 | [5 empty] | 0 | 0 | 0 | -154526.3 | OK | OK | OK | OK | OK | OK | [5 empty] | 0 | 0 | 0
86-LES ORMES-MON BRICO LES ORMES-363,565KWC | GATARD IMMOBILIER | 272673,8 | 327208.56 | 0,2 | 229045,99000000002 | 274855.188 | 52353.372 | OK | 229045,994 | [5 empty] | 0 | 0 | 0 | -272673.8 | OK | OK | OK | OK | [7 empty] | 0 | 0 | 0
|  |  | 0 |  |  | 0 | 0 | OK | [6 empty] | 0 | 0 | 0 | 0 | [11 empty] | 0 | 0 | 0
|  |  | 0 |  |  | 0 | 0 | OK | [6 empty] | 0 | 0 | 0 | 0 | [11 empty] | 0 | 0 | 0
|  |  | 0 |  |  | 0 | 0 | OK | [6 empty] | 0 | 0 | 0 | 0 | [11 empty] | 0 | 0 | 0
|  |  | 0 |  |  | 0 | 0 | OK | [6 empty] | 0 | 0 | 0 | 0 | [11 empty] | 0 | 0 | 0
|  |  | 0 |  |  | 0 | 0 | OK | [6 empty] | 0 | 0 | 0 | 0 | [11 empty] | 0 | 0 | 0
|  |  | 0 |  |  | 0 | 0 | OK | [6 empty] | 0 | 0 | 0 | 0 | [11 empty] | 0 | 0 | 0
|  |  | 0 |  |  | 0 | 0 | OK | [6 empty] | 0 | 0 | 0 | 0 | [11 empty] | 0 | 0 | 0
|  |  | 0 |  |  | 0 | 0 | OK | [6 empty] | 0 | 0 | 0 | 0 | [11 empty] | 0 | 0 | 0
|  |  | 0 |  |  | 0 | 0 | OK | [6 empty] | 0 | 0 | 0 | 0 | [11 empty] | 0 | 0 | 0
|  |  | 0 |  |  | 0 | 0 | OK | [6 empty] | 0 | 0 | 0 | 0 | [11 empty] | 0 | 0 | 0
|  |  | 0 |  |  | 0 | 0 | OK | [6 empty] | 0 | 0 | 0 | 0 | [11 empty] | 0 | 0 | 0
|  |  | 0 |  |  | 0 | 0 | OK | [6 empty] | 0 | 0 | 0 | 0 | [11 empty] | 0 | 0 | 0
|  |  | 0 |  |  | 0 | 0 | OK | [6 empty] | 0 | 0 | 0 | 0 | [11 empty] | 0 | 0 | 0
|  |  | 0 |  |  | 0 | 0 | OK | [6 empty] | 0 | 0 | 0 | 0 | [11 empty] | 0 | 0 | 0
|  |  | 0 |  |  | 0 | 0 | OK | [6 empty] | 0 | 0 | 0 | 0 | [11 empty] | 0 | 0 | 0
|  |  | 0 |  |  | 0 | 0 | OK | [6 empty] | 0 | 0 | 0 | 0 | [11 empty] | 0 | 0 | 0
|  |  | 0 |  |  | 0 | 0 | OK | [6 empty] | 0 | 0 | 0 | 0 | [11 empty] | 0 | 0 | 0
|  |  | 0 |  |  | 0 | 0 | OK | [6 empty] | 0 | 0 | 0 | 0 | [11 empty] | 0 | 0 | 0
|  |  | 0 |  |  | 0 | 0 | OK | [6 empty] | 0 | 0 | 0 | 0 | [11 empty] | 0 | 0 | 0
|  |  | 0 |  |  | 0 | 0 | OK | [6 empty] | 0 | 0 | 0 | 0 | [11 empty] | 0 | 0 | 0
|  |  | 0 |  |  | 0 | 0 | OK | [6 empty] | 0 | 0 | 0 | 0 | [11 empty] | 0 | 0 | 0
|  |  | 0 |  |  | 0 | 0 | OK | [6 empty] | 0 | 0 | 0 | 0 | [11 empty] | 0 | 0 | 0
|  |  | 0 |  |  | 0 | 0 | OK | [6 empty] | 0 | 0 | 0 | 0 | [11 empty] | 0 | 0 | 0
|  |  | 0 |  |  | 0 | 0 | OK | [6 empty] | 0 | 0 | 0 | 0 | [11 empty] | 0 | 0 | 0
|  |  | 0 |  |  | 0 | 0 | OK | [6 empty] | 0 | 0 | 0 | 0 | [11 empty] | 0 | 0 | 0
|  |  | 0 |  |  | 0 | 0 | OK | [6 empty] | 0 | 0 | 0 | 0 | [11 empty] | 0 | 0 | 0
|  |  | 0 |  |  | 0 | 0 | OK | [6 empty] | 0 | 0 | 0 | 0 | [11 empty] | 0 | 0 | 0
|  |  | 0 |  |  | 0 | 0 | OK | [6 empty] | 0 | 0 | 0 | 0 | [11 empty] | 0 | 0 | 0
|  |  | 0 |  |  | 0 | 0 | OK | [6 empty] | 0 | 0 | 0 | 0 | [11 empty] | 0 | 0 | 0
|  |  | 0 |  |  | 0 | 0 | OK | [6 empty] | 0 | 0 | 0 | 0 | [11 empty] | 0 | 0 | 0
|  |  | 0 |  |  | 0 | 0 | OK | [6 empty] | 0 | 0 | 0 | 0 | [11 empty] | 0 | 0 | 0
|  |  | 0 |  |  | 0 | 0 | OK | [6 empty] | 0 | 0 | 0 | 0 | [11 empty] | 0 | 0 | 0
|  |  | 0 |  |  | 0 | 0 | OK | [6 empty] | 0 | 0 | 0 | 0 | [11 empty] | 0 | 0 | 0
|  |  | 0 |  |  | 0 | 0 | OK | [6 empty] | 0 | 0 | 0 | 0 | [11 empty] | 0 | 0 | 0
|  |  | 0 |  |  | 0 | 0 | OK | [6 empty] | 0 | 0 | 0 | 0 | [11 empty] | 0 | 0 | 0
|  |  | 0 |  |  | 0 | 0 | OK | [6 empty] | 0 | 0 | 0 | 0 | [11 empty] | 0 | 0 | 0
|  |  | 0 |  |  | 0 | 0 | OK | [6 empty] | 0 | 0 | 0 | 0 | [11 empty] | 0 | 0 | 0
|  |  | 0 |  |  | 0 | 0 | OK | [6 empty] | 0 | 0 | 0 | 0 | [11 empty] | 0 | 0 | 0
|  |  | 0 |  |  | 0 | 0 | OK | [6 empty] | 0 | 0 | 0 | 0 | [11 empty] | 0 | 0 | 0
|  |  | 0 |  |  | 0 | 0 | OK | [6 empty] | 0 | 0 | 0 | 0 | [11 empty] | 0 | 0 | 0
|  |  | 0 |  |  | 0 | 0 | OK | [6 empty] | 0 | 0 | 0 | 0 | [11 empty] | 0 | 0 | 0
|  |  | 0 |  |  | 0 | 0 | OK | [6 empty] | 0 | 0 | 0 | 0 | [11 empty] | 0 | 0 | 0
|  |  | 0 |  |  | 0 | 0 | OK | [6 empty] | 0 | 0 | 0 | 0 | [11 empty] | 0 | 0 | 0
|  |  | 0 |  |  | 0 | 0 | OK | [6 empty] | 0 | 0 | 0 | 0 | [11 empty] | 0 | 0 | 0
|  |  | 0 |  |  | 0 | 0 | OK | [6 empty] | 0 | 0 | 0 | 0 | [11 empty] | 0 | 0 | 0
|  |  | 0 |  |  | 0 | 0 | OK | [6 empty] | 0 | 0 | 0 | 0 | [11 empty] | 0 | 0 | 0
|  |  | 0 |  |  | 0 | 0 | OK | [6 empty] | 0 | 0 | 0 | 0 | [11 empty] | 0 | 0 | 0
|  |  | 0 |  |  | 0 | 0 | OK | [6 empty] | 0 | 0 | 0 | 0 | [11 empty] | 0 | 0 | 0
|  |  | 0 |  |  | 0 | 0 | OK | [6 empty] | 0 | 0 | 0 | 0 | [11 empty] | 0 | 0 | 0
|  |  | 0 |  |  | 0 | 0 | OK | [6 empty] | 0 | 0 | 0 | 0 | [11 empty] | 0 | 0 | 0
|  |  | 0 |  |  | 0 | 0 | OK | [6 empty] | 0 | 0 | 0 | 0 | [11 empty] | 0 | 0 | 0
Note on C2: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Dans contrat
Note on D2: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Dans contrat
Note on AH2: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Dans votre comptabilité (le plus récent possible)